## Features
Epic | ID | User Story | Description | Status | Notes
Epic 1: Authentication & Account Access | 1.1 | As a user, I want to log in with my email and password so that I can access my dashboard | User authentication with JWT token management and role-based redirect | implemented
Epic 1: Authentication & Account Access | 1.2 | As a user, I want to reset my forgotten password so that I can regain access to my account | Forgot password, reset password, and set new password flows | not implemented | - Password reset does not seem to work, as logging in with newly set password still throws "Wrong password" error; Issue with token detected (Promise)
Epic 1: Authentication & Account Access | 1.3 | As a system, I want to guard routes based on authentication so that unauthorized users cannot access private pages | Private and public route guards | implemented
Epic 1: Authentication & Account Access | 1.4 | As a visitor, I want to see a landing page so that I can learn about the smart mail tracker platform | Public marketing landing page with hero animation | implemented | - Copy content may need improvement to accurately convey platforms features - Image for analytics and reports not present
Epic 2: Dashboard & Layout | 2.1 | As a user, I want a dashboard layout with role-based navigation so that I can access relevant features | Sidebar with role-based navigation, header with notifications and profile access | implemented | - (Unrelated) List of deactivated users not showing; only active users (Promise)
Epic 2: Dashboard & Layout | 2.2 | As a user, I want to see dashboard statistics so that I can monitor my memo activity | Statistics cards and recent activity feed | implemented | - (Unrelated) Approving memos triggers loading state of also the "Reject" button (done) - Pending approvals on dashboard does not have a loading state (done) - Workflow template selection input has no loading state (done) - "Mark all as read" has no loading state (done) - Under "Workflows Used" stat, remove the active count (done)
Epic 2: Dashboard & Layout | 2.3 | As an admin, I want an overview dashboard so that I can monitor system-wide activity and compliance | Admin-specific statistics and compliance overview | implemented | - Memo awaiting review is counted as memo awaiting approval (Promise) - "Total number of forwards" stat does not change (Promise) - "Avg Completion Hours" stat does not change (Promise) - (Unrelated) mailbox side bar not fixed on scroll (done)
Epic 3: Memo Composition | 3.1 | As a user, I want to compose a memo with subject, body, priority, category, workflow, and recipients so that I can create and send official correspondence | Compose form with attachments, scheduling, public toggle, and draft saving | implemented | - Public toggle feature not available - Loading state of "Send" and "Schedule for later" is triggered on draft save (done) - (Unrelated) A single item on the list of notifications, is always fetched and displayed twice, due to response from server. (Promise) - (Unrelated) No retry mech. workflow select template input, in case of network failure (done) -
Epic 3: Memo Composition | 3.2 | As a user, I want to broadcast a memo so that I can send announcements to a wide audience | Mass/announcement memo user interface | implemented
Epic 4: Mailbox | 4.1 | As a user, I want a mailbox with folders so that I can organize my memos | Sidebar with folder navigation and unread counts | not implemented | - Feature does not exist
Epic 4: Mailbox | 4.2 | As a user, I want to view my inbox so that I can see memos received | Paginated inbox list with search, star, archive, delete, and pin actions | implemented | - (Unrelated) Clicking "Back to Sent" for the message in the top-right corner of a message sends the user to the dashboard instead of the sent page. (done) - Icon number badge should only be displayed when opened. When closed no badge should be displayed. (done) - Memo list in inbox is not paginated (Promise) - (Unrelated) On password change, password change banner does not disappear (done) - (Unrelated) When list of memos in inbox or in other categories fail to load due to network error, the message being shown is a no memo message and not a network error message and a manual retry mechanism.
Epic 4: Mailbox | 4.3 | As a user, I want to view sent memos so that I can track what I have sent | Sent folder list | implemented | - Sent memo list is not paginated (Promise)
Epic 4: Mailbox | 4.4 | As a user, I want to view and edit draft memos so that I can finish them before sending | Drafts folder with edit and cancel actions | partially implemented | - Saving drafts triggers loading state of "Send" button (done) - Draft edit does not include any previously saved attachments for removal - (Unrelated) Clicking the notification items does not take the user to the items details (done)
Epic 4: Mailbox | 4.5 | As a user, I want to star important memos so that I can find them quickly | Starred folder with management actions | implemented | - Memo list in starred is not paginated (Promise)
Epic 4: Mailbox | 4.6 | As a user, I want to archive memos so that I can declutter my mailbox | Archived folder with management actions | implemented | - Memo list in archived is not paginated (Promise)
Epic 4: Mailbox | 4.7 | As a user, I want to read a memo with its replies so that I can see the full conversation | Memo detail view with replies timeline | implemented
Epic 4: Mailbox | 4.8 | As a user, I want to reply to a memo so that I can respond to the sender | Reply modal with recipients, priority, workflow, and category options | implemented
Epic 4: Mailbox | 4.9 | As a user, I want to forward a memo so that I can share it with other recipients | Forward modal with recipient search | implemented
Epic 4: Mailbox | 4.10 | As a user, I want to export a memo to PDF or DOCX so that I can share it externally | Export modal with PDF/DOCX options, preferences, and branding | implemented
Epic 4: Mailbox | 4.11 | As a user, I want to edit an existing draft so that I can update my memo before sending | Draft edit modal | partially implemented | - Issue with attachments; mentioned in 4.4
Epic 4: Mailbox | 4.12 | As a user, I want to cancel a memo so that I can retract it if needed | Cancellation confirmation modal | implemented | - Cancelled memo details still loads (Promise)
Epic 5: Record External Memos | 5.1 | As a user, I want to record an external memo so that I can track incoming hard-copy correspondence | Five-step recording wizard with basic and external memo details | implemented
Epic 5: Record External Memos | 5.2 | As a user, I want to attach documents to a recorded memo so that I can include supporting files | Attachment upload step | implemented
Epic 5: Record External Memos | 5.3 | As a user, I want to assign a recorded memo to a department and role so that it reaches the right people | Department and role assignment step | implemented
Epic 5: Record External Memos | 5.4 | As a user, I want to review and submit a recorded memo so that I can generate its tracking details | Review step, submission, and success screen with QR code and tracking URL | implemented
Epic 6: Memo Tracking | 6.1 | As a user, I want to track a memo's movement so that I can see its status and timeline | Authenticated memo search with movement and activity timeline | implemented | - Change registry office email (Engr. Ekene)
Epic 6: Memo Tracking | 6.2 | As a visitor, I want to track a memo without logging in so that I can verify its receipt via the tracking link | Unauthenticated public tracking page linked by QR code | implemented
Epic 7: External Memo Management | 7.1 | As a user, I want to view an external memo's details so that I can see its content and act on it | External memo detail view with comments and actions | implemented
Epic 7: External Memo Management | 7.2 | As a user, I want to acknowledge and complete an external memo so that I can confirm receipt and action taken | Acknowledge and mark-complete actions | implemented
Epic 7: External Memo Management | 7.3 | As a user, I want to share a memo's tracking ID so that external parties can track it | Share modal with tracking ID copy and trackability toggle | implemented
Epic 7: External Memo Management | 7.4 | As a user, I want to forward an external memo so that I can route it within the organization | Forward modal for external memos | implemented
Epic 7: External Memo Management | 7.5 | As a user, I want to view recorded memos so that I can manage external correspondence | Paginated recorded memo inbox with search and status pills |  | - Search is not dynamic (Promise) -
Epic 8: Workflows | 8.1 | As a user, I want to browse the workflow library so that I can find existing workflows | Workflow overview with search and advanced filters
Epic 8: Workflows | 8.2 | As a user, I want to create a workflow so that memos follow defined approval steps | Workflow builder with steps side panel
Epic 8: Workflows | 8.3 | As a user, I want to edit a workflow so that I can update its approval steps | Workflow edit mode
Epic 8: Workflows | 8.4 | As a user, I want to add and edit workflow steps so that I can assign departments and roles | Step editor with department dropdown and role assignment
Epic 8: Workflows | 8.5 | As a user, I want to use workflow templates so that I can start from prebuilt structures | Template gallery with preview modal
Epic 8: Workflows | 8.6 | As a user, I want to view workflow details so that I can understand its features and progress | Workflow detail view with steps and metrics
Epic 9: Administration | 9.1 | As an admin, I want a central console so that I can manage the entire platform | Administration shell with tabbed management views
Epic 9: Administration | 9.2 | As an admin, I want to add and edit users so that I can manage the user base | User CRUD with searchable department dropdown and status control
Epic 9: Administration | 9.3 | As an admin, I want to create and edit roles with permissions so that I can control access | Two-step role editor with permission assignment
Epic 9: Administration | 9.4 | As an admin, I want to manage departments so that I can organize the institution | Department list with add, edit, and delete
Epic 9: Administration | 9.5 | As an admin, I want to manage memo categories so that memos can be classified | Category grid with add, edit, toggle, and delete
Epic 9: Administration | 9.6 | As an admin, I want to view system activity logs so that I can monitor usage and audit actions | Paginated system log viewer with detail view
Epic 9: Administration | 9.7 | As an admin, I want to bulk upload users so that I can onboard many staff quickly | Excel/multipart bulk user upload
Epic 9: Administration | 9.8 | As an admin, I want to view recorded memo statistics so that I can monitor external correspondence | External memo statistics view
Epic 9: Administration | 9.9 | As an admin, I want to configure system settings so that I can control backups, registration, sessions, and security | Auto-backup, registration, session timeout, password policy, and 2FA settings
Epic 10: Department Self-Service | 10.1 | As a department head, I want to manage my department members so that I can assign roles and add members | Member table with search, pagination, add-members modal, and role assignment
Epic 10: Department Self-Service | 10.2 | As a department head, I want to create and edit roles within my department so that I can organize duties | Department role creation and editing modals
Epic 10: Department Self-Service | 10.3 | As a user, I want to view my department members so that I can see colleagues | Read-only department view with members and department memos
Epic 11: Reports & Analytics | 11.1 | As a user, I want to see report statistics so that I can monitor memo performance at a glance | Statistics cards with report tab shell
Epic 11: Reports & Analytics | 11.2 | As a user, I want performance analytics so that I can track top categories and priorities | Performance tab with rankings
Epic 11: Reports & Analytics | 11.3 | As a user, I want workflow analytics so that I can monitor workflow usage and health | Workflow report tab with usage and health metrics
Epic 11: Reports & Analytics | 11.4 | As a user, I want compliance reports so that I can monitor approvals and scheduled memos | Compliance tab with overview, approvals, and scheduled views
Epic 11: Reports & Analytics | 11.5 | As an admin, I want user analytics so that I can track user activity and engagement | Identity-driven user statistics
Epic 12: User Directory (Admin) | 12.1 | As an admin, I want to view all users so that I can review the user base | Paginated users table with actions and memo viewing
Epic 12: User Directory (Admin) | 12.2 | As an admin, I want to view a specific user's memos so that I can audit activity | Per-user inbox and sent tabs
Epic 12: User Directory (Admin) | 12.3 | As an admin, I want to view all memos in the system so that I can monitor memo flow | All memos feed
Epic 12: User Directory (Admin) | 12.4 | As an admin, I want to view any memo's detail so that I can review workflow progress | Admin memo detail with workflow step status rendering
Epic 13: Profile & User Settings | 13.1 | As a user, I want to update my profile, avatar, and signature so that my information is current | Profile edit with avatar and signature upload
Epic 13: Profile & User Settings | 13.2 | As a user, I want to change my password so that I can keep my account secure | Password change with validation | implemented
Epic 13: Profile & User Settings | 13.3 | As a user, I want a settings hub so that I can manage security, appearance, and integrations | Settings tabs for profile, notifications, security, appearance, integrations, and system | implemented
Epic 14: Notifications | 14.1 | As a user, I want to receive notifications so that I stay informed of memo activity | Notification feed with unread count and admin check | implemented
Epic 14: Notifications | 14.2 | As a user, I want to configure notification preferences so that I can control how I am notified | Email, push, quiet hours, and digest settings panel
Epic 15: Activity Logs | 15.1 | As a user, I want to view my own activity logs so that I can review my actions | Personal activity log with action pills | implemented
Epic 16: Export Utilities | 16.1 | As a user, I want to export a memo as a PDF so that I can share print copies | PDF print pipeline with sanitized filenames | implemented
Epic 16: Export Utilities | 16.2 | As a user, I want to export a memo as a DOCX so that I can edit it in a word processor | DOCX generation with logo and branding | implemented

## Summary
Smart Mail Tracker Feature Tracking — Summary
Total Epics | 16
Total User Stories | 67
Status | Count
Implemented | 33
Partially Implemented | 2
Not Implemented | 2
(blank) | 30
Stories per Epic | Count
Epic 1: Authentication & Account Access | 4
Epic 2: Dashboard & Layout | 3
Epic 3: Memo Composition | 2
Epic 4: Mailbox | 12
Epic 5: Record External Memos | 4
Epic 6: Memo Tracking | 2
Epic 7: External Memo Management | 5
Epic 8: Workflows | 6
Epic 9: Administration | 9
Epic 10: Department Self-Service | 3
Epic 11: Reports & Analytics | 5
Epic 12: User Directory (Admin) | 4
Epic 13: Profile & User Settings | 3
Epic 14: Notifications | 2
Epic 15: Activity Logs | 1
Epic 16: Export Utilities | 2